Rove Health

React Native App — Intern Onboarding & Execution Plan

July 2026 (v2)  ·  Team of 3  ·  ~4 weeks build + 1 week rollout  ·  complete app, nothing deferred

# Welcome — what you are building

Rove Health is a women’s health app: cycle tracking, phase-based wellness plans, AI chat, and learning content, live at rovehealth.in and on the Google Play Store.

The current Android app is a thin shell that loads the website inside a webview — every screen downloads over the network, so it feels slow. Your job: rebuild it as a true native app with React Native (Expo SDK 54) so screens live on the phone and open instantly.

Important: the backend does not change. Same Supabase database, same user accounts, same API routes. You are rebuilding the screens, not the product. And this is a complete rebuild — every feature of the current app ships in v1; nothing is left for “later”.

# The complete screen inventory (31 destinations, ~26 native builds)

This list comes from a code audit of the website. If it is not on this list, it is not in scope; if it is, it ships.

| Area | Screens | Count |
| --- | --- | --- |
| Auth | Login, Signup, Forgot password, Reset password | 4 |
| Onboarding | One flow, 5 steps: Welcome, Intro, About You, History, Goals | 5 |
| Core routes | Home hub (“Daily Flow River”), Tracker (18 logging cards — biggest screen), Plan, Plan phase detail, Insights (5 cards + charts), Learn, Learn article reader, Profile (3 sub-sections), Wellbeing intro, Wellbeing assessment | 10 |
| Full-screen experiences (hidden inside pages on web; own screens in the app) | AI chat with voice (largest component), Guided workout session player, Rove Chef, Exercise builder, Workout history, Plan setup wizard | 6 |
| Webviews (one reusable in-app browser screen) | Shop, Science, Story, Ingredient glossary, Privacy, Privacy pledge | 6 dest. / 1 build |
| Not needed | Marketing landing page; splash/loading/error are part of the app shell | — |

One template, four costumes: Home, Plan, Plan-phase, and Tracker are single screens whose content, artwork, and accent colors change with the cycle phase (menstrual / follicular / ovulatory / luteal). You build them once — but you must test them four times (see ground rule 5).

# Day 1 — get set up

Work through this checklist before touching any feature. Ask for access the moment something is missing — don’t wait.

- Install Node 20+, git, and the Expo Go app on your phone.

- Get access to: the GitHub repo, the Expo/EAS organization, and Supabase (read access). Track C also needs Google Play Console access.

- Clone the repo and switch to the migration branch: git checkout react-native-migration

- Install and run: cd mobile && npm install && npx expo start — scan the QR code with Expo Go. You should see the Rove app skeleton on your phone.

- Read docs/react-native-migration-plan.md (technical decisions) and docs/react-native-migration-team-plan.md (the schedule this document is based on).

- As a team: review, test, and commit the work already sitting uncommitted in mobile/ (auth screens and five UI components) so everyone starts from the same known state.

## Where things live

| Folder | What it is |
| --- | --- |
| mobile/ | The new React Native app — this is where you work (pinned to Expo SDK 54) |
| frontend/src/ | The existing Next.js website — your reference for every screen; do not modify |
| shared/ | Pure TypeScript business logic (cycle math) used by both web and mobile |
| backend/, supabase/ | Backend — do not modify |
| docs/ | The migration plans and this document’s source |

# Ground rules (non-negotiable)

- Never modify frontend/ or backend/. The website and its users must be completely unaffected. The one exception is the shared-logic extraction in week 1, which must keep every existing web test green.

- Feature branches + pull requests. Branch off react-native-migration, open a PR, get a review before merging. Never merge your own PR. The branch must always build and run in Expo Go. Stay on Expo SDK 54 — do not upgrade the SDK mid-project (Expo Go on the founder’s iPhone supports 54).

- Same identity everywhere. Same Supabase project, same package name com.rovehealth.app, same API routes on rovehealth.in.

- Every checkpoint happens on a real phone. Emulator-only is never enough; final Android verification needs a physical Android device.

- Four-phase testing rule. For phase-aware screens (home hub, plan, plan phase detail, tracker), the side-by-side checkpoint must be run in all four cycle phases — temporarily adjust the cycle start date on a test account to land in each phase. A bug can hide in just one variant (e.g. longer luteal content overflowing a layout).

- The current Play Store app stays live until the new app has fully rolled out. Don’t delete or break the Capacitor project.

- Commit daily, ask early. Stuck for more than 30 minutes? Post in the team chat with what you tried. Being blocked silently is the only real way to fall behind.

# Team tracks

Each intern owns a track end-to-end. Track A is also integration lead: every PR touching mobile/src/components/ui goes through them, so the design system stays consistent.

| Track | Focus | Owns |
| --- | --- | --- |
| A | Design system & core screens | UI kit, theme parity, tracker, home hub, plan + phase detail, insights. Integration lead for shared UI. |
| B | Auth & user flows | Auth, onboarding, profile, wellbeing, plan setup wizard, workout history, marketing webviews, EAS/analytics setup. |
| C | Platform & risk | Risk spikes (voice, charts), shared-logic package, AI chat, learn, Rove Chef, exercise builder, guided session player, native polish, release. |

# The 4-week schedule

## Week 1 — Foundation, risk, first screens (Days 1–5)

- Day 1 (everyone): setup checklist above; commit the existing uncommitted work. Track C verifies the Play Store signing key the same day (Play Console → Setup → App signing) and backs up any keystore in two places — the one irreversible risk in the whole project.

- Days 1–3 — A: finish the design system: theme tokens from globals.css, fonts, remaining UI kit (sheets, dialogs, selects, toasts). Component-gallery demo screen matching the web side-by-side.

- Days 1–3 — B: finish auth: SecureStore sessions, rovehealth:// deep links, error states. Checkpoint: real login survives killing and reopening the app.

- Days 1–3 — C: risk spikes: ElevenLabs voice (mic permissions, streaming audio) and one chart in victory-native. If voice fails, the fallback decision (webview voice screen) is made by end of Day 3.

- Days 4–5 — A: start the tracker (18 logging cards — budget 4 days).

- Days 4–5 — B: start onboarding (5 steps); verify saved data shows up on the website under the same account.

- Days 4–5 — C: shared-logic package (cycle math, schemas) imported by both web and mobile; the full existing web test suite must pass. A and B stub imports until this lands, then switch.

## Weeks 2–3 — All screens (Days 6–15)

| Days | Track A | Track B | Track C |
| --- | --- | --- | --- |
| 6–8 | Finish tracker (4-phase check) | Finish onboarding (6–7); Profile (8–9) | AI chat incl. voice (streaming, markdown) |
| 9–10 | Home hub (4-phase check) | Wellbeing intro + assessment (10) | Learn + article reader |
| 11–13 | Plan + phase detail (4-phase check) | Plan setup wizard (11); Workout history (12–13) | Rove Chef (11–12); Exercise builder (13) |
| 14–15 | Insights (charts) | Marketing webviews (14 — a test shop order must complete); EAS build profiles + PostHog + error reporting (15) | Guided workout session player |

Checkpoint for every screen: side-by-side with the website on the same account — same data, same numbers. Phase-aware screens: all four phases. A screen merges only after this check passes.

## Week 4 — Polish, testing, release candidate (Days 16–20)

- Days 16–17 — A: visual QA pass on every screen, including the four-phase sweep.

- Days 16–17 — B: write and start the full manual test checklist.

- Days 16–17 — C: native polish: splash screen, status bar, app icons, offline caching (MMKV + TanStack Query persist), push-notification scaffolding. Checkpoint: airplane-mode test — app opens with cached data.

- Days 18–19 (everyone): bug bash on real devices (including at least one real Android phone), Maestro e2e tests for login / tracker / chat, fix everything found. No new features after Day 17.

- Day 20: signed release build uploaded to the Play Console internal testing track. Whole team + founder install from the Play Store link and re-run the checklist.

## Week 5 — Rollout

- Staged rollout 10% → 50% → 100%, watching crash-free rate and analytics between steps.

- Everyone on bug-fix duty; anything not release-blocking goes to a backlog.

- In parallel (nearly free with Expo): iOS TestFlight build → App Store as a fast-follow.

# If things slip

| If… | Then… |
| --- | --- |
| Voice spike fails (Day 3) | The voice screen ships as an in-app webview (the feature still works for users); native voice is revisited after launch. Costs zero days. |
| Tracker takes longer than 4 days | B or C picks up the home hub so A stays on the tracker. |
| Screens run over in weeks 2–3 | The build phase extends by up to 3 days. The testing week (Days 16–20) is never compressed — a complete app means complete quality too. |
| Play review is slow | Nothing to do — it’s Google’s clock. Use the time on the iOS build. |

# Weekly check-ins with the founder

- End of each week: the founder installs the latest build and personally runs that week’s checkpoints on their phone. Their sign-off gates the next week.

- Day 3: the founder is the tiebreaker on the voice fallback decision if the spike fails.

- Day 20: the founder approves the internal-track build before the staged rollout begins.

Questions between check-ins go to the team chat. When in doubt, over-communicate — a two-line message saves a two-day misunderstanding. Welcome aboard!